## Slide 1: Presentation for Quarterly Review Meeting
Initiatives under NPCDCS
Group I

## Slide 2
National Programme for Prevention and Control of Cancer, Diabetes, Cardiovascular Diseases and Stroke (NPCDCS) under NHM
Being implemented, with focus on :
  strengthening infrastructure
  human resource development
  early diagnosis
  management and referral.

## Slide 3
NPCDCS - Pattern of assistance
Assistance to states/ UT is mainly provided for program implementation. The per unit approved costing norm is as under:
S. N. | Type of facility | Costing norm (Rs in Lakh) | 
 |  | Recurring | Non-recurring
1 | State NCD Cell | 105 | 5
2 | District NCD Cells | 32 | 5
3 | District NCD Clinics | 37 | 11
4 | Cardiac Care Units (CCU) | 25.64 | 155
5 | District Day Care Centres |  | 
6 | CHC NCD Clinics | 17 | 9

## Slide 4: Progress under the programme
Sl. No. | Type of facility | Approved | Functional
1 | State NCD Cell | 36 | 36
2 | District NCD Cells | 688 | 543
3 | District NCD Clinics | 706 | 585
4 | Cardiac Care Units (CCU) | 251 | 168
5 | District Day Care Centres | 276 | 168
6 | CHC NCD Clinics | 5351 | 3084

## Slide 5
Issues for discussion:
  A large number of approved facilities are yet to be made functional.
  State Govts. should make the approved facilities functional so that benefits start reaching people.
Less Than 50% facilities functional | 
Infrastructure | Name of States
District NCD clinics | Telangana, Lakshadweep and Delhi
CHC NCD Clinics | Bihar, Goa, Jammu & Kashmir, Kerala, Odisha, Telangana, Tripura, West Bengal, Dadra Nagar & Haveli and Delhi
CCUs | Chhattisgarh, Jammu & Kashmir, Bihar, Goa, Jharkhand, Kerala, Odisha, Tripura and Lakshadweep
Day Care Centres | Andra Pradesh, Bihar, Chhattisgarh, Jharkhand, Tamil Nadu, Telangana, Tripura, West Bengal, Lakshadweep and Puducherry

## Slide 6
Issues for discussion (contd..):
Low utilization of allocated resources : In the financial year 2018-19: Total 23 states spent <50% of allotted budget :
  Group I States (12 States): Bihar, Delhi, Himachal Pradesh, Jharkhand, Jammu & Kashmir, Meghalaya, Nagaland, Odisha, Puducherry, Telangana, Tamil Nadu and Tripura
Lack of human resources at clinic / delay in hiring manpower
Non- availability of equipment, delayed and lengthy procurement processes
Service delivery: lack of systematic referral and follow up
Lack of proper mechanism for reporting data
Involvement of the manpower in multiple programs

## Slide 7: Population-based Prevention initiative for prevention, Screening and Control of common NCDs
Population Level imitative for prevention, control & screening for common NCDs being implemented as a part of comprehensive primary health care.
Persons more than 30 years of age are targeted for screening for common NCDs. Screening services are being provided through trained frontline workers
Referral support and continuity of care are through PHC, CHC, District Hospitals and other tertiary care institutions.
Population Based Screening (PBS) critical for early stage of detection of NCDs. Also useful in generating awareness on the risk factors of NCDs.
Currently PBS has been approved in 219 districts – need to be expanded to remaining Districts
1,55,084 ASHAs, 37,584 ANM/MPWs, 10,135 Staff nurses and 11,024 Medical officers have been trained on screening of common NCDs.

## Slide 8: Comprehensive Primary Health Care - NCD Application
An IT platform to monitor and supervise PBS and to ensure continuum of care
Pre-requisites for successful roll-out of the application :
  Procurement/availability of tablets for ANMs
  IT infrastructure at different levels of health facilities upto District level
  Training of health professionals in use of the application
States being assisted financially for procurement of tablets and other IT infrastructure
Deployment support, including training of health personnel, being provided by Tata Trusts

## Slide 9: Comprehensive Primary Health Care - NCD Application
Status of use of NCD application
So far, 1,19,817 tablets have been procured.
In 5 States/UTs, (Delhi, West Bengal, Lakshadweep, Uttarakhand, and Rajasthan) procurement process has not progressed at all.
In many States/UTs the tablets procured is too less in comparison to the requirement.
19736 Health Professionals trained on NCD Application till 17th September, 2019 across Pan India.
Six states namely Andhra Pradesh, Gujarat, Himachal Pradesh, Kerala, Tamil Nadu, Dadra & Nagar Haveli using their own NCD software application. One time data from these states successfully migrated in GOI NCD Application, prospective data is not getting updated on real-time basis.
Till the first week of 17th September, 2019, total enrolment through NCD application is 8.36 crore and 1.30 crore were screened.

## Slide 10
Issues:
26 states have procured tablets of which few of them have procured tablet much lesser than required (Odisha, Chhattisgarh, Jharkhand, Telangana, Kerala, TN UP, Gujarat, MP, Maharashtra, and AP).
Five States/UTs have not procured tablets (Delhi, West Bengal, Lakshadweep, Uttarakhand, and Rajasthan).
While Total number of Tablets procured stands at 1.19 lakhs, the number of ANMs using tablet regularly is only about 14300 (about 12%).
Usage of Application by the Medical Officers has not taken off. Less than 2,000 MOs are found using the NCD Application.
States need to come forward for any requirement for conducting training of field functionaries.
Need for regularly review of status of usage of NCD application by States/UTs.

## Slide 11: THANK YOU

## Slide 12
Annexure I |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Dist NCD Cells |  | Dist NCD Clinics |  | CHC NCD Clinics |  | Cardiac Care Centre |  | Day care centre | 
 |  | Total Districts | Total approved Districts till 2019-20 | Total Established District NCD Cell till March 2019 | Total approved Districts till 2019-20 | Total Established District NCD Cell till March 2019 | Total approved Districts till 2019-20 | Total Established District NCD Cell till March 2019 | Total approved Districts till 2019-20 | Total Established District NCD Cell till March 2019 | Total approved Districts till 2019-20 | Total Established District NCD Cell till March 2019
 | State/ UT |  |  |  |  |  |  |  |  |  |  | 
1 | Andhra Pradesh | 13 | 13 | 13 | 13 | 13 | 80 | 193 | 12 | 7 | 12 | 0
2 | Bihar | 38 | 38 | 38 | 38 | 30 | 63 | 0 | 12 | 6 | 22 | 0
3 | Chhattisgarh | 27 | 27 | 27 | 27 | 27 | 170 | 89 | 6 | 1 | 11 | 2
4 | Goa | 2 | 2 | 1 | 2 | 2 | 9 | 4 | 2 | 2 | 2 | 2
5 | Himachal Pradesh | 12 | 12 | 12 | 12 | 12 | 9 | 146 | 5 | 11 | 7 | 11
6 | Jammu & Kashmir | 22 | 22 | 14 | 22 | 14 | 81 | 36 | 14 | 6 | 7 | 5
7 | Jharkhand | 24 | 24 | 23 | 24 | 21 | 110 | 68 | 3 | 1 | 7 | 0
8 | Kerala | 14 | 14 | 14 | 14 | 14 | 317 | 85 | 13 | 4 | 14 | 16
9 | Nagaland | 11 | 11 | 11 | 11 | 11 | 5 | 5 | 1 | 1 | 1 | 2
10 | Odisha | 30 | 30 | 30 | 30 | 30 | 382 | 62 | 14 | 5 | 12 | 30

## Slide 13
Annexure I |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Dist NCD Cells |  | Dist NCD Clinics |  | CHC NCD Clinics |  | Cardiac Care Centre |  | Day care centre | 
 |  | Total Districts | Total approved Districts till 2019-20 | Total Established District NCD Cell till March 2019 | Total approved Districts till 2019-20 | Total Established District NCD Cell till March 2019 | Total approved Districts till 2019-20 | Total Established District NCD Cell till March 2019 | Total approved Districts till 2019-20 | Total Established District NCD Cell till March 2019 | Total approved Districts till 2019-20 | Total Established District NCD Cell till March 2019
 | State/ UT |  |  |  |  |  |  |  |  |  |  | 
11 | Sikkim | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 1
12 | Tamilnadu | 32 | 32 | 32 | 32 | 32 | 664 | 664 | 32 | 32 | 32 | 0
13 | Telangana | 31 | 14 | 12 | 30 | 7 | 74 | 21 | 2 | 2 | 7 | 1
14 | Tripura | 8 | 8 | 8 | 8 | 8 | 56 | 23 | 2 | 0 | 2 | 0
15 | West Bengal | 27 | 27 | 27 | 27 | 27 | 293 | 38 | 10 | 8 | 14 | 1
16 | Dadar and Nagar Haveli | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
17 | Lakshadweep | 1 | 0 | 0 | 1 | 0 | 3 | 0 | 1 | 0 | 1 | 0
18 | NCT of Delhi | 11 | 11 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Puducherry | 4 | 3 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 1 | 0
20 | Meghalaya | 7 | 7 | 4 | 7 | 4 | 14 | 8 | 1 | 1 | 1 | 2

## Slide 14: Annexure-2
SN | STATES | Total Districts | Total PHCs | Total SCs | Tablets in hand | Trained Personnel | Total ANMs | Total active ANMs | Total active MO's | Enrolment | Screening | Action to be discussed and planned
1 | Bihar | 38 | 1899 | 9499 | 3144 | 514 | 20583 | 148 | 0 | 18129 | 1225 | Only 15% of ANMs are having the tablets and hence procurement needs to be accelerated Need to focus on the training and boost the enrolment and screening Focus on MO portal
2 | Chhattisgarh | 27 | 785 | 5186 | 700 | 552 | 7430 | 239 | 66 | 837369 | 632827 | Tablets availability is less and needs to accelerate the procurement Training on NCD app also needs to be increased once the tabs are in place
3 | Delhi | 11 | 5 | 10 | 0 | 20 | 85 | 0 | 0 | 19 | 11 | Procurement of Tablets to be initiated Training on NCD App to be planned along with Tablet availability Enrolment and screening to be accelerated MO portal training & usage to be boosted
4 | Goa | 2 | 24 | 214 | 14 | 271 | 357 | 9 | 14 | 10494 | 4137 | Procurement of Tablets to be boosted Training on NCD App to be planned along with Tablet availability Enrolment and screening to be accelerated MO portal training & usage to be boosted
5 | Jammu & Kashmir | 22 | 637 | 2967 | 350 | 207 | 6342 | 21 | 0 | 3663 | 494 | Procurement of Tablets to be boosted Training on NCD App to be planned along with Tablet availability Enrolment and screening to be accelerated MO portal training & usage to be boosted

## Slide 15
6 | Meghalaya | 11 | 109 | 436 | 50 | 82 | 2202 | 27 | 3 | 47562 | 3756 | Need to procure tablets, as state has very few tablets Need to focus on the training and to boost the enrolment and screening Focus on MO portal training
7 | Nagaland | 11 | 126 | 396 | 20 | 26 | 1441 | 1 | 0 | 3827 | 1416 | Procurement of Tablets to be boosted Training on NCD App to be planned along with Tablet availability Enrolment and screening to be accelerated MO portal training & usage to be boosted
8 | Odisha | 30 | 1280 | 6688 | 7088 | 1146 | 10441 | 1030 | 134 | 4150034 | 2208116 | In Odisha, new enrolment and screening has gown down ion past two months. The state need to boost enrolment and screening through NCD drive. ANM Activeness has been reduced to 10% and needs to boost up the enrolment and screening
9 | Sikkim | 4 | 24 | 147 | 64 | 89 | 481 | 31 | 5 | 38340 | 7458 | Procurement of Tablets to be boosted Training on NCD App to be planned along with Tablet availability Enrolment and screening to be accelerated MO portal training & usage to be boosted
10 | Telangana | 31 | 689 | 4797 | 8000 | 4884 | 8817 | 4887 | 314 | 9431464 | 6106759 | Data migration is completed Need to maintain the sustainability of enrolling and screening momentum Need to understand the MO portal operational status
11 | Tripura | 8 | 93 | 987 | 70 | 209 | 1797 | 0 | 0 | 15909 | 2 | Procurement of Tablets to be boosted Training on NCD App to be planned along with Tablet availability Enrolment and screening to be accelerated; only 2 were screened out of enrolled MO portal training and usage to be boosted
12 | Dadra & Nagar Haveli | 1 |  | 71 | 147 | 0 | 132 | 0 | 0 | 1 | 0 | Need to start training, boost the enrolment and screening Focus on MO portal training

## Slide 16
13 | West Bengal | 19 | 914 | 10369 | 0 | 0 | 19211 | 0 | 0 | 0 | 0 | Procurement of Tablets to be initiated Training on NCD App to be planned along with Tablet availability
14 | Jharkhand | 24 | 3848 | 297 | 6000 | 1181 | 9189 | 185 | 2 | 42098 | 5019 | One third of ANMs are not having the tablets and hence needs to boost the procurement Training needs to be boosted and accelerate the enrolment and screening State needs to plans for NCD drive
15 | Lakshadweep | 14 | 4 | 3 | 0 | 0 | 76 | 0 | 0 | 0 | 0 | Procurement of Tablets to be initiated Training on NCD App to be planned along with Tablet availability
16 | Puducherry | 4 | 40 | 81 | 9 | 300 | 404 | 6 | 1 | 1160 | 591 | Procurement of Tablets to be boosted Training on NCD App to be planned along with Tablet availability Enrolment and screening to be accelerated MO portal training & usage to be boosted
States using their own application |  |  |  |  |  |  |  |  |  |  |  | 
17 | Andhra Pradesh | 13 | 1147 | 7458 | 12298 | 0 | 16201 | 0 | 0 | 2201202 | 13 | 
18 | Himachal Pradesh | 12 | 538 | 2083 | 2000 | 24 | 2813 | 0 | 0 | 1079165 | 607234 | 
19 | Kerala | 14 | 849 | 5380 | 9600 | 4 | 5626 | 0 | 0 | 652449 | 16936 | 
20 | Tamil Nadu | 32 | 1835 | 8712 | 1454 | 55 | 0 | 0 | 0 | 2244626 | 2244626 |