## Slide 1: Presentation for Quarterly Review Meeting
Strengthening of Tertiary care cancer facilities scheme (TCCC/SCI)
Group II

## Slide 2
Tertiary Care Cancer facilities scheme under NPCDCS
Setting up of State Cancer Institute (SCI)/Tertiary Care Cancer Centre (TCCCs) supported under the scheme.
Rs. 120 Crore per SCI and Rs. 45 Crore per TCCC – to be shared between Central and State Governments in 60:40 ratio (90:10 in case of NE and hilly States)
Till March 2018, 35 proposals (15 SCIs & 20 TCCCs) have been approved programme. In addition, two more SCIs – at Jabalpur and Jammu – have been approved in 2019-20
Issues:
Early completion of sanctioned projects – No States has sought release of second installment .It implies that activities envisaged in the scheme are yet to be completed
Non-submission of UCs by State Governments
Further release of Central assistance to be on reimbursement basis.
State Govts to ensure utilization of Central assistance already released and seek further funds on reimbursement basis
As extension of the scheme is upto March, 2020, all the State Government must ensure timely completion of sanctioned projects during the current financial year.

## Slide 3
S No | State | Name of Institute (SCI/TCCC) | Total Amount Recommended (Equip.+ Cons) | Central share released | State share released | Status of procurement of Equipments | Status of Construction/Civil Work | Functional/ Completion of project (%age)
1 | Assam | Gauhati Medical College & Hospital, Guwahati, SCI | Rs.119.90 cr. (Equip: Rs. 88.20 cr. Cons: Rs. 31.70 cr.) | Rs. 80.932 cr. (Rs. 08.43 cr. during 2016-17, Rs. 30.00 cr. during 2017-18 and Rs. 42.5025 during 2018-19) | Rs. 3.85 cr. | Operation Micorscope, 3D-4D USG machine, Vedeo Endoscopy with ERCP, Pathology lab installed. Procurement of Dosimetry and Surgical Laser Equipment under progress. | Tender process completed for civil work | 100 % functional in existing building.
2 | Gujarat | Gujarat Cancer Research Institute, Ahmedabad, SCI | Rs. 120.00 cr. (Equip: Rs. 105.84 cr. Cons: Rs. 14.16 cr.) | Rs. 67.50 cr. (2014-15) | Rs. 22.51 cr. | 67 equipment installed. PO issued for 72 equipments. | 1A +1B building complete. 1C building to be completed by December, 2019. | 80 %
3 | Haryana | Civil Hospital, Ambala Cantt, TCCC | Rs. 45 cr. (Equip: Rs. 33.40 cr. Cons: Rs. 11.6 cr.) | Rs. 20.25 cr. [Rs. 9.2253 cr. during 2016-17, Rs. 2.925 cr. during 2017-18 and Rs. 8.0997 cr. during 2018-19] | Rs. 8.1 cr. | Procurement of LINAC, Brachytherapy, CT Simulator etc. to be done by HLL & MoU signed in September, 2017. | Structural work complete. 1st & 2nd Floor flooring completed. Electrical panel installation, HVAC work under progress. | -
4 | Karnataka | Kidwai Memorial Institute of Oncology (RCC), Bangaluru, SCI | Rs. 120.00 cr. (Equip: Rs. 115 cr. Cons: Rs. 5.0 cr.) | Rs. 67.50 cr. | Rs. 48.00 cr. | Majority of equipment including Robotic Surgery System, High Energy LINAC procured. LC opened for HDR Brachytherapy & CT Simulator. | Work related to Construction of Radiotherapy wing with LINAC Bunkers, Electrical power supply etc. completed. | 96 %
Status of projects for setting up SCIs and TCCCs (Group-II) – Annexure III

## Slide 4
S No | State | Name of Institute (SCI/TCCC) | Total Amount Recommended (Equip.+ Cons) | Central share released | State share released | Status of procurement of Equipments | Status of Construction/ Civil Work | Functional/ Completion of project (%age)
5 | Karnataka | Mandya Institute of Medical Sciences, Mandya, TCCC | Rs. 45.00 cr. (Equip: Rs. 33 cr. Cons: Rs. 12 cr.) | Rs. 17.257 cr. (2015-16) | Rs. 12.75 cr. | Tender floated for LINAC Dosimeters & mould Equipments. | 80% of main block civil construction is over, Electrical work yet to start. | 50%
6 | Madhya Pradesh | G.R. Medical College, Gwalior, TCCC | Rs. 42.00 cr. (Equip: Rs. 35 cr. Cons: Rs. 7 cr.) | Rs. 18.90 cr. (2017-18) | - | Nil | Under progress | -
7 | Madhya Pradesh | Netaji Subhas Chandra Bose Medical College, Jabalpur, SCI | Rs. 120.00 cr. (Equip: Rs. 84 cr. Cons: Rs. 36 cr.) | Rs. 17.299 cr. (2019-20) | Not yet reported by the Institute (SCI has been approved and funds released during August 2019) |  |  | 
8 | Maharashtra | Rashtrasant Tukdoji Regional Cancer Hospital & Research Centre, Nagpur, TCCC | Rs. 44.991 cr. (Equip: Rs. 31.339 cr. Cons: Rs. 13.66 cr.) | Rs. 20.176 cr. [Rs. 15.32 cr. during 2016-17 and Rs. 4.8564 during 2017-18] | Rs. 9.258 cr. | Majority equipment including HDR machine, CT Simulator, Mammography, X ray etc. installed. | Infrastructure work for CT Scan room, chemo day care ward, Modular OT completed. | 100% compliance in Equipment purchase. 80% compliance in Construction.
9 | Maharashtra | Government Medical College, Aurangabad, SCI | Rs. 96.70 cr. (Equip: Rs. 69.78 cr. Cons: Rs. 26.92 cr.) | Rs. 43.515 cr. (2017-18) | Rs. 27.49 cr. | Administrative approval for approved equipments has been obtained & procedure to procure the same is in process. | Administrative approval obtained. Final DPR prepared by HSCC India Ltd. work will start soon. | -
Status of projects for setting up SCIs and TCCCs (Group-II) – Annexure III

## Slide 5
S No | State | Name of Institute (SCI/TCCC) | Total Amount Recommended (Equip.+ Cons) | Central share released | State share released | Status of procurement of Equipments | Status of Construction/ Civil Work | Functional/ Completion of project (%age)
10 | Maharashtra | Vivekanand Foundation & Research Centre, Latur, TCCC | Rs. 45.00 cr. (Equip: Rs. 43.50 cr. Cons: Rs. 1.5 cr.) | Rs. 20.25 cr. (2017-18) | Rs. 8.205 cr. | Majority of equipment including CT Scan, MRI machine, Computerised Radiography System etc. installed. Brachytherapy HDR installation in progress. | No New construction at present. | 60%
11 | Mizoram | Mizoram State Cancer Institute, Aizawl TCCC | Rs. 44.27 cr. (Equip: Rs. 29.08 cr. Cons: Rs. 15.19 cr.) | Rs. 14.64 cr. (2015-16) | Rs. 1.623 cr. | Purchase order for LINAC made on 16.08.16 | 100% of civil works (Bunker for LINAC). 40% of electrification & other works. | -
12 | Punjab | Government Medical College, Amritsar SCI | Rs. 114.61 cr. (Equip: Rs. 74.51 cr. Cons: Rs. 40.10 cr.) | Rs. 51.58 cr. (2016-17) | Rs. 3.122 cr. | Process for machinery and equipment purchase has been started | Construction of main SCI block started and 25% of foundation work completed. | -
13 | Punjab | Civil Hospital, Fazilka TCCC | Rs. 44.71 cr. (Equip: Rs. 33.30 cr. Cons: Rs. 11.41 cr.) | Rs. 20.119 cr. 2016-17) | Rs. 1.28 cr. | In process | - | Would be functional by March 2020
Status of projects for setting up SCIs and TCCCs (Group-II) – Annexure III

## Slide 6
S No | State | Name of Institute (SCI/TCCC) | Total Amount Recommended (Equip.+ Cons) | Central share released | State share released | Status of procurement of Equipments | Status of Construction/ Civil Work | Functional/ Completion of project (%age)
14 | Rajasthan | S P Medical College, Bikaner TCCC | Rs. 38.05 cr. (Equip: Rs. 29.15 cr. Cons: Rs. 8.9 cr.) | Rs. 17.123 cr (2015-16) | Not reported by the Institute | High Energy LINAC purchased and installation under process. | Bunker for High Energy LINAC, Room for CT Simulator, Brachytherapy completed. Bunker for Low Energy LINAC under construction. | 60%
15 | Rajasthan | SMS Medical College, Jaipur SCI | Rs. 119.25 cr. (Equip: Rs. 83.25 cr. Cons: Rs. 36 cr.) | Rs. 44.8077 cr. [Rs. 40.6683 cr during 2016-17 and Rs. 4.1394 cr. during 2017-18] | Rs. 5.00 cr. | Tender floated for 2 LINAC and 1 CT Simulator. | Basement and Ground floor finishing in progress. Outer development and ramp work in progress. | Almost 96% of construction has been completed & equipment are being procured.
16 | Rajasthan | Jhalawar Medical College & Hospital, Jhalawar TCCC | Rs. 43.90 cr. (Equip: Rs. 38.90 cr. Cons: Rs. 5.00 cr.) | Rs. 19.755 cr. (2017-18) | Rs. 25 lakhs | Few equipments has already been procured i.e. Biochemistry, Microbiology, X ray machine, 64 Slice CT Scan through other budget sources. Other equipments will be procured after starting construction work. | Tender has been decided by Implementation Agency- RSRDC. At proposed site for construction, old T.B. Hospital building has been dismantled. Civil work to start soon. | Tender has been decided by Implementation Agency- RSRDC. At proposed site for construction, old T.B. Hospital building has been dismantled. Civil work to start soon.
17 | Uttar Pradesh | Sanjay Gandhi Postgraduate Institute of Medical Sciences, Lucknow TCCC | Rs. 45.00 cr. (Equip: Rs. 45.00 cr. Cons: Nil) | Rs. 11.43 cr. (2015-16) | Rs. 7.62 cr. | Purchase of LINAC and RT network system and TPS under progress. | No major construction. Minor renovations and modifications completed. | No major construction. Minor renovations and modifications completed.
Status of projects for setting up SCIs and TCCCs (Group-II) – Annexure III